## Sheet1
CW = Calendar Week Demo = Prezentare clienti | Done in time | Done with delay | Not done | Planned
| CW1 | CW2 | CW3 | CW4 | CW5 | CW6 | CW7 | CW8 | CW9 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15
Selectie echipe | bar: Done in time CW1
Selectie proiect/companii | bar: Done with delay CW2
Discutie setat despre asteptari/clarificari | bar: Not done CW3
Pregatire enviroment(mediu de lucru, limbaj) | bar: Planned CW5
S 6,7-defisheye&format,denoising,white-balance | bar: Planned CW6 to Planned CW7
S 8- 4 scalare,auto exposure correction | bar: Planned CW8
Demo initial | bar: Planned CW9
Ultimele retusuri/blackbox
Demo final | bar: Planned CW14
Finalizat activitate | bar: Planned CW15